## Refresh Methodology
|  | Scenario: "The refresh of QA system from the production system counts with 1:1 copying of existing archive from production to QA system.” Prerequisites: 1. Tasks list assumes that all production data/objects are included in the refresh (tables with following prefixes: /DVD/*, ADMI*, ZARIX*, AIND*) 2. Archiving processes must be finished and be in consistent state before refresh 3. Central system for SNP OutBoard Housekeeping and regular archiving processes is SAP Solution Manager System scenario: QA and PRD SAP systems |  | Method for copying archive data during the system refresh with the filter The copy of the data between storages must be 1:1, retaining the names of files as well as containers. If only certain specific files should be copied, then identify corresponding ones using following relationship: i.AKD arch. files: ADMI_FILES-ARCH_DOCID = /DVD/CRP_SMCCMAP-DOC_ID; ii./DVD/CRP_SMCCMAP-SM_CONTAINER_ID is the subfolder name in AWS S3 while /DVD/CRP_SMCCMAP-SM_PACKID is the file name.
Area | Task # | Mandatory/Optional | Task (Step) | Responsible | Comment | Due Date | Due Time | Duration [h]
Before system refresh
SAP users | REF-1.1 | Mandatory | Backup of System users configured in QA system | Customer - Basis | System users defined in ICF service and Java Connector must be preserved after the refresh.
ICF Service | REF-2.1 | Mandatory | Backup of SNP OutBoard ICF Service | Customer - Basis | T-code: SICF ICF Service: dvd_crp_http System user ID: TBD Logon Procedure: TBD Note: Backup of customizing is not required if PROD system contains same customizing with the same user credentials
Storage | REF-3.1 | Mandatory | Backup of Storage management & Java connector customizing customizing | Customer - Basis | T-code: /DVD/EM --> Content server --> Storage definition For the storage backup do following: 1. In the toolbar select Tools --> SM Backup 2. Choose a path where to save the backup 3. By default, all required tables are backed up, but it's poosible to expand the selection 4. Click on "Specify table selection" and hit "Key" button for table /DVD/RL_SETTC 5. Specify following values in the field "Tool" of table /DVD/RL_SETTC (SM, CRP & CRP_SMC) 6. Run export data Note: To restore the setup from the backup, open the tool again, choose a backup file, and select the import radio button
| REF-3.2 | Optional | Preserve RFC Destinations | Customer - Basis | T-code: SM59 It is common practice to re-import all RFC destinations during the system refresh. Storage Management is dependent on all required RFC destinations of type G or T for connection to target storage, which needs to be preserved RFC Destination: DATAVARD_JAVA_CONNECTOR Program ID: DATAVARD_JAVA_CONN If the same RFC destinations in entire SAP landscape are setup and PROD RFC is the part of system refresh, no action is required. Otherwise, please preserve configuration of QA RFC destination before the refresh
| REF-3.3 | Optional | Preserve secondary DB connection | Customer - Basis | T-code: DBCO If secondary DB connection is part of the storage configuration, its reimport is required otherwise this task may be skipped.
| REF-3.4 | Optional | Preserve SSL Security certificates | Customer - Basis | T-code: STRUST If security certificates are part of the storage configuration, their reimport is required otherwise this task may be skipped.
| REF-3.5 | Mandatory | Stop Java connector before system refresh | Customer - Basis | T-code: /DVD/JCO_MNG Go to JCO management using transaction /DVD/JCO_MNG, turned on Java Connector marked by a green tick in the column Connection. To stop JCO click on the button Stop all to turn off all Java Connectors or click on the Stop button to stop Java Connector.
| REF-3.6 | Mandatory | Clean the content of QA AWS S3 Storage | Customer - DB Admin | "The refresh of QA system from the production system counts with 1:1 copy of existing archive from production to QA system.” If this is the case, then clean the corresponding content of QA bucket before the load of the content from production bucket.
SNP OutBoard Suite | REF-4.1 | Mandatory | Backup of SNP product license keys | Customer - Basis | Store Product license before system refresh manually or Report: /DVD/RL_UTIL_TABLE_BACKUP The report provides export and import of the table content. For both scenarios, there is a common parameter File path. This parameter points to the file on the local disk to which table content will be exported and vice versa. For Export scenario, you have to specify table selection by clicking on the button Specify table selection. Import scenario provides an option to clean the table content before importing by checkbox Cleanup before import. Table selection: /DVD/TAB_LICENSE
| REF-4.2 | Optional | Preserve SNP OutBoard Source ID customizing | Customer - Basis | Note: If Source ID definition is even in entire SAP landscape, no action is required. Otherwise, please backup below listed tables by using the same report specified in predecessor task REF-4.1 or reimport TR with corresponding customizing. Table selection: /DVD/CRP_SOURCE /DVD/CRP_SOURCET /DVD/CRP_SMC_MAP
| REF-4.3 | Optional | Preserve SNP OutBoard Retention Management custimizing and retention periods | Customer - Basis | Note: Per defualt no action step should be required since SNP OutBoard retention Management customizing should be even in entire SAP landscape. If that is not the case, the customizing should be reimported by using the same report specified in predecessor task REF-4.1 or reimport TR with corresponding customizing. Table selection: /DVD/CRP_RM_FLD /DVD/CRP_RMI_HLD /DVD/CRP_RMI_RET
| REF-4.4 | Optional | Preserve SNP OutBoard Housekeeping configuration | Customer - Basis | No action required if central system of SNP OutBoard Housekeeping is SAP Solution Manager or Production system of ECC/S4 landscape
| REF-4.5 | Optional | Preserve Regular archiving process | Customer - Basis | No action required if central system of SNP OutBoard Housekeeping is SAP Solution Manager or Production system of ECC/S4 landscape
Archiving client | REF-5.1 | Mandatory | Preserve Content repositories definitions | Customer - Basis | T-code: OAC0 Note: In case of usage Logical content repositories concept the backup is not required. Otherwise, please follow below instructions. Before any system refreshes, include all configurations of utilized target content repositories in OAC0 into the workbench transport request and re-import it afterward back. Workbench TR should contain the hostname of the app. server & HTTP port of the refreshing system.
| REF-5.2 | Mandatory | Preserve shared directory shared cross-application servers | Customer - Basis | T-code: FILE Logical file path used in archiving object specific customizing
| REF-5.3 | Optional | Preserve SSL Security certificates requires for HTTPS Content repositories | Customer - Basis | T-code: STRUST If security certificates are part of the content repositories configuration, their reimport is required otherwise this task may be skipped
| REF-5.4 | Optional | Preserve Archiving object specific customizing | Customer - Basis | T-code: AOBJ Note: Per default no action step should be required since archiving object specific customizing should be even in entire SAP landscape. If that is not the case, the customizing of archiving object in the scope must be reimported
| REF-5.5 | Optional | Preserve SARA residence customizing | Customer - Basis | T-code: SARA Note: Per default no action step should be required since SARA residence customizing of desired archiving objects should be even in entire SAP landscape. If that is not the case, the customizing of SARA residence periods must be reimported
System refresh
System refresh | REF-6.1 | Mandatory | Run system refresh | Customer - Basis
After system refresh
ICF Service | REF-7.1 | Mandatory | Reimport SNP OutBoard SICF service customizing | Customer - Basis | T-code: SICF Make sure that definition of SNP OutBoard ICF service is same as before refresh and is active
Storage | REF-8.1 | Mandatory | Upload backed up storage definition | Customer - Basis | T-code: /DVD/EM --> Content server --> Storage definition Run import of tables backed up within the task REF-3.1. Note: Before the upload veridy whether chosen tables are empty in QA system. If not run Cleanup before import
| REF-8.2 | Mandatory | Verify RFC destination | Customer - Basis | T-code: SM59 Verify definition of previously backed up RFC destination
| REF-8.3 | Optional | Verify secondary DB conneciton | Customer - Basis | T-code: DBCO If secondary DB connection is part of the storage configuration, its reimport is required otherwise this task may be skipped.
| REF-8.4 | Optional | Verify presence of required SSL Security certificates | Customer - Basis | T-code: STRUST If security certificates are part of the storage configuration, their reimport is required otherwise this task may be skipped.
| REF-8.5 | Mandatory | Restart Java | Customer - Basis | T-code: /DVD/JCO_MNG Go to JCO management using transaction /DVD/JCO_MNG, turned on Java Connector marked by a green tick in the column Connection. To restart JCO click on the button Restart to turn on Java Connectors. Repeat for all application servers displayed on the screen.
| REF-8.6 | Mandatory | Run storage check | Customer - Basis | T-code: /DVD/EM --> Content server --> Storage definition Open definition of desired storage and hit Check button in toolbar menu
| REF-8.7 | Mandatory | Load the content of production S3 bucket to QA bucket | Customer - DB Admin | The loading of the data in AWS S3 from the productive bucket to QA. The copy must be 1:1, retaining the names of files and containers. The load should be done by provided storage functionalities from storage vendor. Should only certain files be copied -> identify them using following relationship: - AKD arch. files: ADMI_FILES-ARCH_DOCID = /DVD/CRP_SMCCMAP-DOC_ID - /DVD/CRP_SMCCMAP-SM_CONTAINER_ID is the subfolder name in AWS S3 while /DVD/CRP_SMCCMAP-SM_PACKID is the file name.
SNP OutBoard Suite | REF-9.1 | Mandatory | Import back SNP product license keys | Customer - Basis | Report: /DVD/RL_UTIL_TABLE_BACKUP Import scenario provides an option to clean the table content before importing by checkbox Cleanup before import. Table selection: /DVD/TAB_LICENSE
| REF-9.2 | Mandatory | Verify SNP OutBoard Source ID customizing | Customer - Basis | Note: If Source ID definition is even in entire SAP landscape, no action is required. Although if the customizing from any reason has been backed up before refresh, please import below listed tables by using the same report specified in predecessor task REF-9.1 Table selection: /DVD/CRP_SOURCE /DVD/CRP_SOURCET /DVD/CRP_SMC_MAP
| REF-9.3 | Optional | Preserve SNP OutBoard Retention Management custimizing and retention periods | Customer - Basis | Note: Per defualt no action step should be required since SNP OutBoard retention Management customizing should be even in entire SAP landscape. If that is not the case, the customizing should be reimported by using the same report specified in predecessor task REF-9.1 Table selection: /DVD/CRP_RM_FLD /DVD/CRP_RMI_HLD /DVD/CRP_RMI_RET
| REF-9.4 | Optional | Switch SNP OutBoard Housekeeping central system | Customer - Basis | Task assumes that central system for SNP OutBoard Housekeeping is SAP Solution Manager or Production system of ECC/S4 landscape. Run t-code /DVD/ERNA_SWITCH in QA system
| REF-9.5 | Optional | Preserve Regular archiving process | Customer - Basis | No action required if central system of SNP OutBoard Housekeeping is SAP Solution Manager or Production system of ECC/S4 landscape
Archiving client | REF-10.1 | Mandatory | Reimport Content repositories definitions | Customer - Basis | T-code: OAC0 Note: In case of usage Logical content repositories concept the backup is not required. Otherwise, please follow below instructions. Before any system refreshes, include all configurations of utilized target content repositories in OAC0 into the workbench transport request and re-import it afterward back. Workbench TR should contain the hostname of the app. server & HTTP port of the refreshing system.
| REF-10.2 | Mandatory | Verify shared directory shared cross-application servers | Customer - Basis | T-code: FILE Logical file path used in archiving object specific customizing
| REF-10.3 | Optional | Verify presence of required SSL Security certificates for HTTPS content repositories | Customer - Basis | T-code: STRUST If security certificates are part of the content repositories configuration, their reimport is required otherwise this task may be skipped
| REF-10.4 | Mandatory | Activate ArchiveLink certificates for content repositories | Customer - Basis | 1. Firstly delete the content in following transaction: /DVD/EM --> Content Server --> Security Certificate Control 2. Send new ArchiveLink certificates from T-code OAC0 from each desired content repositories 3. Open t-code: /DVD/EM --> Content Server --> Security Certificate Control and activated newly displayed ArchiveLink certificates
| REF-10.5 | Mandatory | Run Content repositories connection test | Customer - Basis | T-code: OAC0
| REF-10.6 | Optional | Run RSCMST report for desired content repositories | Customer - Basis | Report: RSCMST
| REF-10.7 | Mandatory | Verify Archiving object specific customizing | Customer - Basis | T-code: AOBJ Archiving object speciic customizing must be same as before refresh
| REF-10.8 | Mandatory | Verify SARA residence customizing | Customer - Basis | T-code: SARA SARA Residence custmizing must be same as before refresh
| REF-10.9 | Mandatory | Verify the status of all SARI infostructures | Customer - Basis | T-code: SARI Archive infostructures of archiving object in the scope should be activated. The check can be done in corresponding SARI transaction.